## Sheet1
Time-Cost Labor Estimates
WBS ID | Task Description | Estimate (hrs) | Estimating Approach | Estimated Duration (hrs) | Estimated Interruptions (hrs) | Total Duration (hrs) | Labor Rate $/hr | Labor Cost Total $
1.0 | Legal | 80 | Historical |  |  |  |  | 36925
1.1 | Legal - Research current patent filings | 25 | Historical | 37.9 | 8.3 | 46.2 | 250 | 11550
1,2 | Legal - Evaluate Potential for IP Infringement | 20 | Historical | 30.3 | 6.6 | 36.9 | 250 | 9225
1.3 | Legal - Document Reason for Approval | 20 | Historical | 30.3 | 6.6 | 36.9 | 250 | 9225
1.4 | Legal - File Patents | 15 | Historical | 22.7 | 5 | 27.7 | 250 | 6925
2.0 | BD1 - Business Development | 38 | Historical |  |  |  |  | 10530
2.1 | BD1 - Secure Meetings | 10 | Historical | 15.2 | 3.3 | 18.5 | 150 | 2775
2.2 | BD1 - Meeting with Customers | 20 | Historical | 30.3 | 6.6 | 36.9 | 150 | 5535
2.3 | BD1 - Secure Videogame APIs | 6 | Historical | 9.1 | 2 | 11.1 | 150 | 1665
2.4 | BD1 - Deliever APIs to IT | 2 | Historical | 3 | 0.7 | 3.7 | 150 | 555
3.0 | IT1 - Identify - Test Game 1 | 70 | Wide Band |  |  |  |  | 23920.5
3.1 | IT1 - Review Most Popular Game's API | 10 | Wide Band | 15.2 | 3.3 | 18.5 | 185 | 3422.5
3.2 | IT1 - Determine Necessary Coding Requirements | 10 | Wide Band | 15.2 | 3.3 | 18.5 | 185 | 3422.5
3.3 | IT1 - Implement Overlay Code for 1st Game | 40 | Wide Band | 60.6 | 13.2 | 73.8 | 185 | 13653
3.4 | IT1 - Review and Test Overlay for 1st Game | 10 | Wide Band | 15.2 | 3.3 | 18.5 | 185 | 3422.5
4.0 | BD2 - Proof of Concept Definition | 45 | Historical |  |  |  |  | 12465
4.1 | BD2 - Secure Proof of Concept Meetings w/game manufacturers | 5 | Historical | 7.6 | 1.7 | 9.3 | 150 | 1395
4.2 | BD2 - Present Proof of Concept to Manufacturers | 20 | Historical | 30.3 | 6.6 | 36.9 | 150 | 5535
4.3 | BD2 - Begin Negotiating Terms of a Contracts | 20 | Historical | 30.3 | 6.6 | 36.9 | 150 | 5535
5.0 | Contracts | 60 | Historical |  |  |  |  | 23985
5.1 | Contracts - Legal Draft | 40 | Historical | 60.6 | 13.2 | 73.8 | 250 | 18450
5.2 | Contracts - BD Deliver and Review w/Clients | 20 | Historical | 30.3 | 6.6 | 36.9 | 150 | 5535
6.0 | IT2 - Games 2 - 5 | 116 | Historical |  |  |  |  | 39664
6.1 | IT2 - Apply Code to 2nd popular game | 30 | Historical | 45.5 | 9.9 | 55.4 | 185 | 10249
6.3 | IT2 - Review and Test Overlay for 2nd game | 5 | Historical | 7.6 | 1.7 | 9.3 | 185 | 1720.5
6.4 | IT2 - Apply Code to 3rd most popular game | 25 | Historical | 37.9 | 8.3 | 46.2 | 185 | 8547
6.5 | IT2 - Review and Test Overlay for 3rd game | 5 | Historical | 7.6 | 1.7 | 9.3 | 185 | 1720.5
6.6 | IT2 - Apply Code to 4th most popular game | 20 | Historical | 30.3 | 6.6 | 36.9 | 185 | 6826.5
6.7 | IT2 - Review and Test Overlay for 4th game | 5 | Historical | 7.6 | 1.7 | 9.3 | 185 | 1720.5
6.8 | IT2 - Apply Code to 5th most popular game | 20 | Historical | 30.3 | 6.6 | 36.9 | 185 | 6826.5
6.9 | IT2 - Review and Test Overlay for 5th game | 5 | Historical | 7.6 | 1.7 | 9.3 | 185 | 1720.5
6.10 | IT2 - Document and Present Testing Results and any Issues | 1 | Historical | 1.5 | 0.3 | 1.8 | 185 | 333